Cross sector development and delivery of reusable learning objects to support life long learning in Health Sciences and Practice

Short title:

Learning Objects:Lifelong Application (LOLA)

Final Report submitted to Eduserv Foundation

Project details: www.nottingham.ac.uk/nursing/lola

Project Description

"There is too little cross-sector collaboration in supporting learners as they move through the education system - we need a greater focus on linking our public sector systems to provide unified support for learners throughout life." (Towards a Unified e-Learning Strategy: consultation document, 2003)

Despite many UK government policy recommendations [1, 2], cross sector education collaboration involving UK HE and UK FE (post 16 years) are difficult to initiate and sustain for a whole variety of reasons [3]. Agendas such as personalised learning, widening participation and life long learning have highlighted the need for more support for learners moving from one educational sector to another. This Eduserv Foundation (www.eduserv.org) funded project built on an existing successful community of practice that is creating high quality eLearning content for multidisciplinary use in the form of reusable learning objects (RLOs). RLOs are web-based interactive “chunks” of learning material designed to address a single learning objective, outcome or goal that can be used flexibly in teaching and learning programmes. The project (named LOLA - Learning Objects, Lifelong Application) brought together partners from UK Further Education (FE), Higher Education (HE) and the National Health Service (NHS) to work collaboratively on the development of learning objects from concept through to evaluation with students and tutors across the sectors. The project explored the feasibility of working across traditional sectoral boundaries in order to develop a repository of freely available RLOs for students as they moved through the education system, so that students on an Access to HE course at an FE college using a repository of learning objects to support their studies move to university courses and have access to the same repository and a similar set of learning objects (albeit at a different academic level). Later on, these individuals would be able to access the repository as qualified health care workers continuing their education in the workplace. A common repository of learning objects to support learning built around a cross sector community could help to support a seamless transition as students move across learning sectors. Two strands of work already underway at Nottingham provided a starting point for the RLO development. Some RLOs in Pharmacology to support a Post-registration Nurse Prescribing course [4] and RLOs on Infection control in Healthcare (a highly topical and important area that needs to be tackled by improving education across all sectors and professional boundaries) had already been produced. This project would produce additional RLOs covering these themes.

- Acknowledgements

The following groups and individuals have made this project possible. The project team: Dr Jo Lymn, Dr Jacqueline Randle, Tim Hills, Mitch Clarke, Wendy Shaw, Leanne Williams, Dr Stephen Timmons and Lucrezia Herman. UCeL and the RLO-CETL collaborations provided expertise to the project, and in particular the Directors - Dawn Leeder and Professor Tom Boyle.  The following also contributed: Paraskevas Vezirydis, Jacqueline Cahill, Dr Richard Windle, Mr Fred Riley, Natalie Vaughan, Fiona Bath-Hextall, Sarah Dennis (Vice Principal Castle College), Lynette Lall, Rob Cutforth, Raj Pandya, Will Campion, Fiona Bath-Hextall, the FE lecturers who took part in the RLO workshop. Many lecturers and students who have peer reviewed and evaluated the RLOs for us.

- Project Aim

The LOLA project aim was to collaboratively develop a set of ‘mature’ RLOs that represented the lifelong learning continuum (FE to HE to continuing professional development as an employee in the UK National Health Service (NHS)). The RLOs would be catalogued and housed in an ‘open’ repository along with all the media assets.

The project also addressed the following questions:

- What 'added value' will RLOs bring to the wide range of learners and their tutors across sectors?

- How reusable will RLOs be across a range of educational settings and levels?

- How can this collaborative, multi-institutional approach be made to be successful?

- Project Team Members

The core project team consisted of two lecturers from the HE sector Dr Joanne Lymn and Dr Jacqueline Randle; two NHS employees, Tim Hills a senior pharmacist and Mitch Clarke - a senior infection control nurse who both delivered professional development sessions to NHS staff and medical students, and two Health and social care lecturers from a local FE College Wendy Shaw and Leanne Williams. All these members were content experts in the areas of infection control and pharmacology and were responsible for writing the RLOs. They also ensured that the RLOs were embedded in their own courses and acted as brokers for promoting the RLOs to other colleagues. Dr Heather Wharrad was the principal investigator and Dr Stephen Timmons the co-investigator and research lead. Lucrezia Herman was the project media developer and Fred Riley the learning technologist who built the LOLA repository. However many other individuals and groups contributed to the project (see acknowledgements).

- Executive summary

The project has provided an opportunity to explore the opportunities and barriers for cross sector development of RLOs and a shareable repository that will support lifelong learners in health-care. This was a small scale local study but by focussing on two key themes, infection control and pharmacology, there are some legacy outputs in the form of 15 high quality multimedia RLOs and over 80 media assets all freely available under a Creative Commons licence for educational use stored in a purpose built open repository (www.nottingham.ac.uk/nursing/lola ). There is evidence of extensive reuse of the RLOs worldwide. Student feedback indicates that these resources are providing added value to their learning, and students are recommending the RLOs to others. This project faced some of the same challenges reported in other cross sector initiatives [5,6]. The different institutions and sectors have different priorities; institutional reorganisation and change can impact on collaborative projects. Findings from interviews show that the participants involved in the project were very enthusiastic about the idea of cross-sector collaboration, a shared repository and community development of RLOs.

- Project Outputs

  - 15 RLOs

15 peer reviewed, IMS compliant, high quality multimedia RLOs are a key output of this project. Table 1 summarises the learning outcomes covered by each RLO and outlines some of their technical and pedagogical features. All the RLOs with one exception use a media player incorporated within HTML pages originally designed for the RLO-CETL by Rob Cutforth the RLO-CETL learning technologist (2005-2006). The media player houses the text, audio commentary and Flash and video components of the RLO and provides the navigational control buttons including pause/play, move forward and back to other sections and an option to increase the animation screen size. Additional navigation is provided by clickable tabs indicating the content and activities for each section. The design template and functionality was informed by feedback from users of previous RLO designs developed by this team where students indicated they wanted to be able to stop and start the RLO and know how much of the RLO they had completed at any point. All RLOs had text, audio, Flash components and animations, at least one activity and self assessment, a glossary and links to other resources. In the RLOs where a clinical skill was being demonstrated video clips were incorporated alongside the animations. The RLOs were made publicly available via a url link on the SONET (www.nottingham.ac.uk/nursing/sonet ) and LOLA  (www.nottingham.ac.uk/nursing/lola ) websites until the LOLA repository had been built (see section 5.3); the IMS content packages are available from the LOLA repository.

Table 1 RLO showcase – Descriptions of RLOs developed

NB Text and audio commentary are standard features of all the RLOs listed.

Difficulty is rated on a 4 point star scale where * signifies the RLO with the easiest and **** the most difficult concepts

|  | Learning outcome | Narrative screens | Animation sequences (secs) | Activities | Assessments | Additional Media | Learning time and difficulty |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Aseptic Non-Touch Technique | Introduces the concept of ANTT, used to prevent infection during clinical procedures; includes a video demonstration. | 2 | 116 | 1 drag and drop | 1 MCQ quiz | Flash animation 5.5 min Video clip | 15 min ** |
| Bacteria and viruses compared | Introduces and compares the structural components of bacteria and viruses by allowing users to "build" their own. | 3 | 159 | 2 drag and drop | 1 fill in the gap | Flash animations | 15 min * |
| Glove use | Examines appropriate glove use in a variety of clinical scenarios, with a video demonstration of the correct procedure for putting on sterile gloves. | 4 | 165 | 1 drag and drop | 1 select correct answers | Flash animations 1 min Video clip | 15 min ** |
| Home hazards | Reconstructs a room visited by a local health visitor in 2005. The student's task is to identify the areas of concern noted by the health visitor. | Narrative appears as feedback whilst working through activity | N/A | Select 8 areas on image provided | 1 MCQ quiz | Flash presentation | 10 min * |
| Introduction to drug clearance | Provides a definition of clearance, and a basic explanation of the factors which influence it. | 3 | 252 | 1 drag and drop; 1 drag the cursor | 1 Blockbuster style quiz game | Flash animation | 15 min *** |
| Pharmacokinetic and pharmacodynamic influences of aminoglycoside dosing | Examines how the absorbtion and distribution of aminoglycosides within the body affects the dosing regimens used. | 4 | 245 | 2 activities – select points on graphs | 1 MCQ quiz | Flash animation | 20 min **** |
| The inflammatory response | Introduces stages in the inflammatory response. | 4 | 144 | 1 drag and drop | 1 MCQ quiz | Flash animation | 15 min ** |
| Volume of distribution | Explains the pharmacological concept of Vd, and how it is calculated. | 2 | 241 | 1 drag and drop | 1 MCQ quiz | Flash animation | 15 min **** |
| Clinical impact of changes in drug clearance | Examines some of the factors which affect total body clearance of a drug and how this, in turn, influences a drug's clinical impact. | 5 | 356 | 1 drag and drop 1 select option for feedback | 1 crossword | Flash animation | 15 min *** |
| General Adaptation Syndrome | Explores the role of stress in triggering disease, detailing and critiquing the three phases of General Adaptation Syndrome as first proposed by Hans Selye. | 5 |  |  |  | Flash animation | 15min ** |
| Personal Protective Equipment (PPE) | Examines when and how to use personal protective equipment in clinical and other settings. | 4 | 195 | 1 drag and drop | 1 Drag and drop assessment | Flash animation | 10min * |
| Prokaryotes and Eukaryotes | Explains the characteristics of prokaryotic and eukaryotic cells | 5 | 198 | 1 drag and drop | 1 Drag and drop | Flash animation | 10 min * |
| Sizes and scales | Compares units of measurement such as mm, cm, m and shows how to convert between them | 6 | 224 | 1 drag and drop | 1 select the correct answer | Flash animation | 10 min * |
| Childhood Obesity | Examines the issue of childhood obesity from the perspectives of the biomedical, behavioural and socio-economic models of health. | 5 | 427 | Select the right model | crossword | Flash animation | 10 min ** |
| Body Mass Index | Explains why body mass index is used and how it is calculated | 2 |  | calculation | MCQ | Flash animation | 10 min ** |

  - Development Templates and evaluation tools adapted for cross sector use

A set of templates and tools were used at various stages of the development (Development Methodology framework - Appendix 2) and evaluation process (Evaluation framework and toolkit - Appendix 4). These forms and documents were originally developed by the UCeL and RLO-CETL management groups and were adapted for use across sectors in the LOLA project. The set comprises: RLO specification form, peer review 1 form, peer review 2 form, student evaluation questionnaire, online questionnaire, tutor context of learning form, evaluation of learning effectiveness form. In addition a set of interview questions to explore cross sector working on the LOLA project was produced (Appendix 5). These tools are available on the LOLA website and completed specification and peer review forms relating to each RLO are located next to the RLO link.

  - Custom built LOLA learning repository

At the time of writing the original bid the requirements for the repository could have been satisfied by simply putting the RLOs and selected assets up on a web site, but this would be a poor 'solution'. By "repository" we mean:

a public database of RLOs and selected assets which allows end-users to browse/search for resources by keyword, subject, classification, etc, and from which they can download the RLOs and individual assets

LOLA repository requirements (available at www.nottingham.ac.uk/nursing/lola) were drawn up by Fred Riley (School of Nursing Learning Technologist) who built the database to house the LOLA RLOs http://www.nottingham.ac.uk/nursing/lola/repository/ after considering two proprietary options:

Equella was considered as it was the local system used by the University of Nottingham and there would be an advantage in having local on-site support. However, even implementing simple deposition and search/browse facilities required significant time developing forms and functionality from scratch using Equella's proprietary scripting language. This involved extensive collaboration with the University’s IS Learning Team comprising some tens of hours on trying to customise Equella to LOLA requirements to no avail.

RLO-CETL Installation of Intrallect's Intralibrary repository system, though very good from the deposition viewpoint, lacked a public end-user search/browse interface. At the time of evaluation, Intralibrary required users to be logged into the system to access resources, and we wanted LOLA materials to be openly available to the public. Neither was there an automatic user self-registration option which could have fulfilled this requirement - instead, users had to be created manually by an administrator. In addition, the search/browse interface in Intralibrary is intimidating for non-technical users unfamiliar with repositories and metadata issues.

RLOs were packaged using RELOAD and catalogued with the UK LOM Core Metadata Schema as they incorporate instructional design and pedagogy. The media assets (see 5.4)  do not have any educational content and were catalogued using the simpler Dublin Core. Metadata input was kept as simple as possible. The RLOs required 15-30 minutes each to catalogue. Assets were catalogued within 5 minutes or less each.  End-users can browse and search the LOLA records by:

- title

- keyword

- description

- file type (eg JPG, SWF)

  - 80 Media Assets

In addition to the RLOs available as complete learning packages, the component assets in the form of Flash and bitmap images have also been uploaded into the repository and available under the Creative Commons licence. There are over 80 reusable images, tagged to allow discovery using key words. These assets have wider, general applicability beyond the main themes of infection control and pharmacology. We have also incorporated a Tag Cloud of keywords to aid discovery of appropriate images (see examples Appendix 3)

http://www.nottingham.ac.uk/nursing/lola/repository/

- Project Outcomes

  - Evaluation data on usage, usability and value of the RLOs

6.1.1 Usage (from RLO online feedback form)

Table 2 shows the usage patterns for eight of the RLOs (as of October 2008 - these change daily). The completion of the online feedback form is optional so these data are an underestimate of overall use. The ‘Visits’ parameter shows those who have clicked on the feedback tab and we can make the assumption that they have been through the RLO, but of these only a small number chose to complete the feedback form (‘Completes’ column).

The lead HE Institution is using the RLOs more than the other partners (Figure 1) but there is evidence of considerable reuse of particular RLOs outside of the project partners. This reuse extends to institutions all over the world (see Appendix 9).

Table 2 Usage statistics for 8 RLOs

|  | Visits | Completes | Univ | NHS | FEColl | Other |
| --- | --- | --- | --- | --- | --- | --- |
| Vol. of Distribution | 174 | 18 | 3 | 0 | 0 | 13 |
| Home Hazards | 162 | 19 | 1 | 0 | 16 | 1 |
| ANTT | 683 | 159 | 51 | 4 | 6 | 66 |
| Glove use | 328 | 53 | 25 | 4 | 7 | 6 |
| Bacteria & Viruses | 234 | 24 | 10 | 0 | 6 | 5 |
| Inflammatory Res | 274 | 62 | 21 | 2 | 7 | 24 |
| Intro to clearance | 21 | 2 | 2 | 0 | 0 | 0 |
| Aminoglycosides | 187 | 9 | 3 | 0 | 0 | 5 |

6.1.2 Ratings of RLOs

The charts in Figure 1 show that the RLOs are rated very highly overall and are easy to use and helpful for learning. Nearly all respondents would use the RLOs again and recommend them to others. In answer to ‘What did you like most?’ the 217 comments from 349 respondents, were organised around seven themes: Specific media-video, animations, audio (49%); Interactivity, assessment & feedback (32%); Level & understanding (20%); Versatility, ease of use (15%); Length, pace & ‘chunks’ (11%); Clinical application/awareness (11%); Engaging, fun (8%). Fewer comments were offered in answer to the question ‘What did you not like?’. The themes related to Technical and access problems (33%); Incorrect practice technique in video (22%); Too simple/too short (22%); Too advanced or detailed (13%); Improve level of assessment/examples (10%). A selection of direct quotes illustrating each theme can be found in Appendix 6.

6.2 Lecturers’ perspectives and Context of Learning

Lecturers gave feedback on the RLOs and their context of use by completing online feedback forms for individual RLOs as described in section 6.1.1. And also by completing Context of Learning forms (see examples in Appendix 7) – these provided information about how the RLOs were being used in specific modules. To raise awareness of the RLOs and the LOLA project with FE lecturer’s, members of the LOLA project team ran a staff development workshop at the College (Summary in Appendix 8; Full report on the website).

Figure 1 Online Feedback from 348 end users of the LOLA RLOs (data has been summated for eight RLOs). 212 users classified themselves as Students, 99 as staff and 37 as Other. Staff and Other included health care workers from various NHS Trusts around the UK.

6.3 Research data on the cross sector collaboration

The HE and NHS Trust project members tended to work more closely together on the RLO production than did the FE college lecturers. This involved reviewing each other’s storyboards and media prototype or by jointly authoring the storyboards. Two rounds of qualitative interviews were conducted with all of the project participants, at the mid-point and end of the project. These interviews were used to gain a better understanding of the process of cross-sector collaboration, and to get a picture of what were the factors that facilitated or constrained collaboration. Data from the interviews are still being analysed. Preliminary findings show that the participants were very enthusiastic about the idea of cross-sector collaboration, and believe that it had worked well. However, there had been constraints at the level of the institution, where resources had not always allowed participants to devote as much time to RLO development as they felt it needed. In the case of one of the participating institutions, there had been major organisation change, which had also been inimical to collaboration and the development of RLOs. A full report will be posted on the LOLA website.

7.0 Benefits for the wider community

There is evidence that the project and its outputs have benefited the wider community well beyond the immediate project team. This has been facilitated by the open access repository and easy access to RLOs via the LOLA and SONET websites, deposition of the RLOs in JORUM, RLO-CETL repository and INTUTE and by dissemination (see section 8.0). A list of some of the institutions who have indicated that they are accessing the RLOs is shown in Appendix 9. It has been noted that the Facebook social networking site has been used by students to draw their peers’ attention to the LOLA RLOs – the extent of this activity is unknown.  A number of institutions have requested the IMS content packages, for example Queen Mary’s University of London have added the Aseptic Nontouch technique RLO to their CETL Learning and Clinical Communication Skills website http://www.cetl.org.uk/learning/tutorials.html ; also Derbyshire Mental Health Trust; Jonkoping University Library, Sweden, and the University of Stavanger, Norway.

8.0 Dissemination

The LOLA project has been disseminated widely, both nationally and internationally. LOLA RLOs have been demonstrated at many CETL, HEA and NHS workshop events as well as at national and international elearning, and health conferences. The table below sets out dissemination outputs with URLs for access to presentations and posters.

| Date | Output |
| --- | --- |
| 2005 |  |
| 27th April | The Eduserv Foundation Symposium 2005 Many for Many: Collaborative e-Resource Development and Use Presentation: www.nottingham.ac.uk/nursing/lola/dissemination/ |
| 2006 |  |
| 22-23rd June | Collaborative Elearning Symposium University of Cambridge Learning Object Showcase presentation: demonstration of LOLA RLOs |
| 2007 |  |
| 5th January | Launch symposium of the Centre for Health care associated diseases. Poster presentation and prize with travel award of £150 Poster: www.nottingham.ac.uk/nursing/lola/dissemination/ |
| 5th June | Annual conference ‘Inspiring Researchers’ Nottingham university Hospitals NHS Trust Abstract: www.nottingham.ac.uk/nursing/lola/dissemination Presentation: www.nottingham.ac.uk/nursing/lola/dissemination |
| 10-12th December | RLO-CETL Wolfson Workshop CARET University of Cambridge RLOs in Health Demonstration Presentation: www.nottingham.ac.uk/nursing/lola/dissemination |
| 18th December | A repository of pharmacology multimedia learning objects for pre-registration and post-registration medical and nursing courses HJ Wharrad, R Windle, M Taylor, L Herman, T Hills, B Leighton, A Mostyn, R Robinson, JS Lymn British Pharmacological Society Meeting Brighton E-journal of the BPS vol 5 issue 2 at http://www.pa2online.org/abstract/abstract.jsp?abid=28786&author=wharrad&cat=-1&period=33 Abstract: www.nottingham.ac.uk/nursing/lola/dissemination Poster:www.nottingham.ac.uk/nursing/lola/dissemination |
| 2008 |  |
| 2nd September | Castle College of FE Staff Development Workshop Reusable Learning Objects and the LOLA project Presentation: www.nottingham.ac.uk/nursing/lola/dissemination |
| 9th-11th September | Elearning Resources for Health ALT-C University of Leeds Demonstration Stand. LOLA Publicity leaflet: www.nottingham.ac.uk/nursing/lola/dissemination |
| 17-18th November | How easy is cross sector collaboration? A case study of the collaborative development of elearning in infection control, medicines and prescribing. H. Wharrad, L. Herman, S. Timmons, J. Randle, J. Lymn, W. Shaw, L. Williams, T. Hills, M. Clarke, International Conference of Education, Research and Innovation (ICERI 2008) Madrid. Paper: www.nottingham.ac.uk/nursing/lola/dissemination Presentation: www.nottingham.ac.uk/nursing/lola/dissemination |
| 21st November | Presentation by H Wharrad at HEA Health Sciences and Practice E-learning special interest group. ‘RLOs are good for health: collaborative approaches’ at University of West of England, Bristol Presentation: www.nottingham.ac.uk/nursing/lola/dissemination |
| Annually | Presentations at University of Nottingham new lecturers PGCHE events |

9.0 Achievement of aims

We had proposed to develop 20 ‘mature’ RLOs and there were a number of reasons why this was not achieved:

- The target of 20 RLOs was too ambitious for a cross sector project; this rate of development has been achieved within the host HE institution and in HE collaborative projects.

- Some of the RLOs explained difficult concepts and it took longer to design the appropriate analogies with more complex animations than expected.

- There were a number of external factors that slowed up progress on the project right at the start including major institutional reorganisation in two of the sectors and some health problems of team members.

- The peer review process which is so important for quality assurance, slowed up development because we were relying on goodwill of colleagues to review the RLOs for us at two stages of the process. With busy workloads this was not a priority, an incentive such as payment for reviewers might have helped.

- Apart from the first meeting, it was never possible to get the whole project team together; communication became more ‘virtual’ as the project progressed. Communication by email is not always efficient particularly when trying to describe subtle amendments to RLO animations.

10.0 Sustainability and Future Projects

The 2008 Cooke report (http://www.dius.gov.uk/policy/documents/online_innovation_in_he_131008.pdf ) on Online Innovation in HE to the Secretary of State for Innovation, Universities and Skills recommends: “a new approach to virtual education based on a corpus of open learning content: the UK must have a core of open access learning resources organised in a coherent way to support on-line and blended learning by all higher education institutions and to make it more widely available in non-HE environments.”   The LOLA project is an example of an open learning cross sector repository albeit on a small scale. Some sustainability of certain strands of the project will be achieved namely the existing RLOs, assets and repository will continue to be accessed by a wide range of lecturers and students world wide. New RLOs will require further funding and further projects building on the LOLA work have already been secured from the NHS Institute for Innovation and Improvement (3 RLOs on Service Improvement in the NHS) and the Hospital Infection Society (an RLO on hand washing for patients and relatives delivered on the bedside entertainment screens). A number of funded projects with the local NHS Trusts are also underway. There are plans to work with Castle College on a JISC institutional call for Institutional Innovation projects in lifelong learning and workforce development (for 9.1.08). Further development of content, tools, pedagogical design and research will continue until 2010 within SONET-ARC at the University Of Nottingham Department Of Nursing (now the School of Nursing, Midwifery and Physiotherapy) as an institutional partner of the RLO-CETL focusing on health. The SONET-ARC itself is now established as a permanent development and research unit within the School of Nursing, Midwifery & Physiotherapy at the University of Nottingham.

References

- DFES (2003) Towards a Unified e-Learning Strategy Consultation Document Available at http://www.dcsf.gov.uk/consultations/downloadableDocs/towards%20a%20unified%20e-learning%20strategy.doc (accessed 1.10.08).

- DFES (2005) Harnessing Technology – Transforming Learning and Children’s Services http://www.dcsf.gov.uk/publications/e-strategy/ (accessed 1.10.08)

- Weiss J (1987) Pathways to cooperation among public agencies. J of Policy Anal. & Management, 7(1) 94-117

- Lymn J, Bath-Hextall F & Wharrad HJ (2008) Pharmacology education for nurse prescribing students - a lesson in reusable learning objects. BMC Nursing, 7(1), 2.

- Hartnell-Young E, Smallwood A, Kingston S and Harley P (2006) Joining up the episodes of lifelong learning: A regional transition project. Br J Ed Tech. 37(6) 853-866

Connelly M, Jones C and Jones N (2007) Managing collaboration across further and higher education: a case in practice. J of Further and Higher Education 31(2

# Footnotes

In early 2002 a number of UK Medical Schools and Schools of Nursing founded a collaborative project to produce a bank of high quality RLOs to support and enhance teaching in the traditionally difficult areas of statistics, epidemiology and research skills. Creation of these resources is very costly; typically amounting to more than one institution can afford. Yet many of these resources are generic and can be used, re-used and shared between institutions and across disciplines. So the Universities’ Collaboration in Elearning’ (UCEL) was founded to create, develop and share these resources (www.ucel.ac.uk). In 2005 the School of Nursing at Nottingham was a partner in the successful bid to become a UK HEFCE Centre for Excellence in Teaching and Learning in Reusable Learning Objects (RLO-CETL www.rlo-cetl.ac.uk) with London Metropolitan University and University of Cambridge (a founder member of UCeL). The aims of the CETL are to develop a structured framework for producing a critical mass of quality-assured RLOs that can be shared and reused throughout higher education.

By mature we mean used extensively by students and embedded into courses across the sectors

The media template was not suitable for the Home Hazards RLO design

A diagram of a heart, for example, only gains educational significance when placed within an educational context, such as a course or textbook.